## Project Tracker
Project | Owner | Status | Start Date | Target Date | Priority | Risk Level | Notes
Platform Reliability Improvements | Alex Rivera | In Progress | 2026-01-15 | 2026-03-30 | High | Medium | Reduce Sev-2 incidents; rollout staged by service; align with SRE.
Q1 Hiring Plan (Backend) | Alex Rivera | Planned | 2026-01-10 | 2026-02-28 | Medium | Low | 2 headcount approvals pending; update interview loops; refresh rubric.
On-Call Rotation Revamp | Alex Rivera | In Progress | 2026-01-20 | 2026-02-20 | High | High | Coverage gaps on weekends; define escalation; pilot follow-the-sun support.
Security Dependency Updates | Alex Rivera | At Risk | 2026-01-05 | 2026-02-15 | High | High | Multiple critical CVEs; coordinate with AppSec; staged rollout with canaries.
Engineering Metrics Dashboard | Alex Rivera | In Review | 2026-01-12 | 2026-02-10 | Medium | Medium | Agree on definitions for velocity/quality; automate data pulls; avoid vanity metrics.
Latency Budget Initiative | Alex Rivera | Planned | 2026-02-01 | 2026-04-15 | Medium | Medium | Define SLOs, error budgets, and enforcement gates on releases.
Developer Experience Tooling | Alex Rivera | In Progress | 2026-01-22 | 2026-03-01 | Medium | Medium | Improve CI times and local dev setup; introduce caching; docs refresh.
Cost Optimization (Cloud Spend) | Alex Rivera | Planned | 2026-02-05 | 2026-04-05 | High | Medium | Identify top cost drivers; optimize storage and compute; set budgets/alerts.
Incident Response Training | Alex Rivera | Planned | 2026-02-10 | 2026-03-10 | Medium | Low | Run tabletop exercises; update playbooks; assign IC rotations.
Service Ownership Boundaries | Alex Rivera | In Review | 2026-01-18 | 2026-02-25 | Medium | Medium | Clarify ownership map; update runbooks; align with SRE and product.
Quarterly OKR Definition | Alex Rivera | Complete | 2026-01-03 | 2026-01-17 | High | Low | OKRs finalized and reviewed with leadership; communicated to team.
Performance Review Calibration Prep | Alex Rivera | In Progress | 2026-02-01 | 2026-03-05 | High | Medium | Compile evidence; draft ratings; coordinate calibration session.
Data Retention Policy Rollout | Alex Rivera | At Risk | 2026-01-28 | 2026-03-15 | High | High | Cross-team dependencies; needs legal review; implement deletion jobs.
Authentication Hardening (MFA) | Alex Rivera | In Progress | 2026-01-25 | 2026-02-20 | High | High | Enforce MFA for privileged actions; audit logs; rollout comms plan.
Team Capacity Planning Model | Alex Rivera | Planned | 2026-02-12 | 2026-03-20 | Medium | Medium | Model capacity vs roadmap; incorporate on-call load; quarterly refresh.
Release Train Experiment | Alex Rivera | In Review | 2026-01-30 | 2026-02-28 | Medium | Medium | Pilot weekly release train; define gates; evaluate impact on incidents.